Details

|  |  |  |
| --- | --- | --- |
| **Venue** | | |
|  | Closed for the whole day for private event | |
|  | Setup time | 1400 – 1600hrs  Setup areas:   * Reception table   To be setup by hired vendor (MarieZarezky)   * Extended outdoor area   Extra tables and chairs (EventsPartner)  Floral Arch (MarieZarezky)   * Grazing table arrangement   Arrangement by Mei   * 2x Wine barrel for solemnization table * Office to be converted to make up / changing room * Empty gin bottles on each table for centrepiece * Extra cups on the tables along the march down aisle for rose petals * Table and chairs arrangement for all the 3 areas * **\*To confirm: Menu card for each table** * **\*To confirm: Fridge for 40cm tall cake** |
|  | Usage time | 1700 – 2359hrs (official hours) |
|  | # of staffs | 2x Bartender \*Mark to be onsite  9x floor staff  4x cook |
| **Signage** | | |
|  | A1 size standee for welcome signage  \*Does not include the signage itself. Couple will provide the signage | |
| **Office for makeup room** | | |
|  | Office to be converted make up room for bride. **Strictly only bride, bridesmaid and Makeup artist allowed to enter.** | |
|  | Items to provide | Long standing mirror  Fully drawn curtain / temp block / wall on the other side for private setting |

|  |  |  |
| --- | --- | --- |
| **Indoor Area** | | |
|  | Denise’s family and relative  1x wheelchair bound Granny  1x special care group of Denise friend (Pregnant) | |
|  | Capacity | 26 + 1(Senior Citizen) pax |
|  | # of tables | 3x booth  2x big table |
|  | # of chairs | 6x chairs |
|  | Grazing table | 2x high table  2x long high table  \*To be placed side by side to make up 3M long table for grazing table |
| **Canopy Area** | | |
|  | Kenny’s family and relative | |
|  | Capacity | 33 + 1(Infant) pax |
|  | # of tables | 1x big table  12x low table |
|  | # of chairs | 25x chair |
|  | Kitchen area | 4x cooks |
| **Extended outdoor area** | | |
|  | Friends | |
|  | Capacity | 60pax |
|  | # of tables | 1x Wine barrel Table (Solemnization)  2x Pallet Table  11x Standing Table |
|  | # of chairs | 16x Crate Stool  32x In House High Chair |

|  |  |  |
| --- | --- | --- |
| **Food** | | |
|  | $2,400 for grazing table  $600 for hot food item | |
|  | Grazing table | **Food items / portion**  • Edamame  • Wakame Seaweed Salad  • Soba Salad – Yuzu Dressing  • Edamame Hummus  • Beetroot Hummus  • Veggie Spring Rolls  • Curry Chicken Dumplings  • Shrimp Shumai  • Fresh Veggies  • Mixed Nuts  • Dried Fruits  • Fresh Fruits  • Assorted Crackers  • Assorted Charcuterie  • Assorted Cheeses  • Gummy Bears  Food item label  **\*To confirm: Wedding cake stand**  **\*To confirm: Disposables plates and utensils** |
|  | Hot food item | 120 portions  **\*Food items to be discussed and finalized in September when head chef is back**  **\*To confirm: Additional portions can be ordered onsite and paid at same rate** |
| **Beverages** | | |
|  | $5000++ for free flow drinks all night  **\*Additional drinks requested on site, not in the list, to be paid separately** | |
|  | Drinks | 1x Champagne bottle  Customized welcome cocktail  Customized Kenny’s cocktail  Customized Denise’s cocktail  Peroni Beer by the bottle  1 choice of Mocktail  Coke  Sprite  Orange juice  Still water |

|  |  |  |
| --- | --- | --- |
| **Wedding favour** | | |
|  | Price / bottle : $23++ | |
|  | Bottled cocktail | 200ml  Customized Kenny’s cocktail  Customized Denise’s cocktail  Event exclusive mocktail   |  |  | | --- | --- | | Her | 46 | | His | 46 | | Mocktail | 13 | |  |  | |
|  | Bottled mocktail | 200ml  Event exclusive mocktail   |  |  | | --- | --- | | Mocktail | 13 | |  |  | |
|  | Label | Tanglin Gin’s label  Customized design  **\*Design to be confirmed in September together with extended outdoor area completion when marketing executive is in** |

|  |  |  |
| --- | --- | --- |
| **Extra table and chair rental** | | |
|  | Extra furniture rental from external vendor to accommodate guests for extended outdoor area  $1500 GST included + transport costs +10% service charge for Tanglin Gin labour  Setup and Teardown supervision and labour to be provided by Tanglin Gin | |
|  | Solemnization Table | 1x WINE BARREL |
|  | Guest Table | 2X PALLET COFFEE TABLE  13X COOPER HIGHTABLE SILVER – BLACK TOP |
|  | Guest Chairs | 16X CRATE STOOL |

|  |  |  |
| --- | --- | --- |
| **Audio / Video** | | |
|  | **\*To confirm: Location of the speaker** | |
|  | # of microphone | 2x wireless microphone |
|  | # of speaker | 2x portable speaker |
| **External vendors** | | |
|  | External vendor engaged for setup of the event | |
|  | Mei | 1400 – 1600 hrs setup  Tables and decoration. Excluding food items.  1630 -1730 hrs setup  Food items |
|  | Tanglin : Events partner | 1400 – 1600 hrs setup  Tables and chairs setup for extended outdoor area |
|  | Marie Zarezky | 1400 – 1600 hrs setup   1. Faux floral arch at extended outdoor area 2. Decoration setup at reception table |
|  | Pixioo | 1730 hrs onwards |
|  | Makeup artist | 1730 – 1900 hrs in office room for bride make up |

|  |  |
| --- | --- |
| **Area layouts** | |
| Rough layout of all table and chair locations for all 3 areas | |
| Indoor |  |
| Canopy |
| Extended outdoor |

Summary

|  |  |  |
| --- | --- | --- |
| **Action pending Tanglin Gin** | | **Due** |
| 1. | Extended outdoor area to be completed latest by 15 September 2022 | 15 Sep  Done✅ |
| 2. | Contact EventsPartner for proposed table and chair rental for extended outdoor area | Predecessor: Activity 1  Done✅ |
| 3. | Revise wedding favour price per bottle from original 200ml spirit -> 200ml cocktail | Together with Activity 2  Done✅ |
| 4. | Setup meeting with marketing executive to discuss wedding favour label design | Before 30 Sep |
| 5. | Setup onsite meeting after head chef is back to confirm onsite food items | Before 30 Sep |
| 6. | Provide venue layout with confirmed furniture / deco / speaker setting | Predecessor: Activity 1  Done✅ |
| 7. | Setup meeting with Mei to confirm on grazing table detail | Best before 31 Aug  Done✅ |

|  |  |  |
| --- | --- | --- |
| **Action pending Couple** | | **Due** |
| 1. | Provide confirmed guestlist | 31 Aug  Done✅ |
| 2. | Confirm area’s group of guest | Predecessor: Tanglin Activity 1  Done✅ |
| 3. | Provide confirmed # of wedding favour | Predecessor: Tanglin Activity 3  Done✅ |
| 4. | Cocktail mixing session with Mark  \*Welcome drink (done)  \*Kenny (done)  \*Denise (done) | 16 Aug  Done✅ |
| 5. | Deposit  \*Predecessor activity: Revised invoice line items and confirmed venue details | After invoice and detail final revision |
| 6. | A1 Welcome sign | 22 Oct |
| 7. | Day schedule  \*So that venue manager will know who to expect at what time | Before 31 Aug  Done✅ |

Quoted prices

|  |  |  |  |
| --- | --- | --- | --- |
| **Description** | **Quantity** | **Unit Price** | **Cost** |
| Venue Rental | 1 | $5,000.00 | $5,000.00 |
| Food Costs | 120 | $20.00 | $2,400.00 |
| Additional Food Costs | 120 | $5.00 | $600.00 |
| Beverage Costs | 1 | $5,000.00 | $5,000.00 |
| 200ml bottled Cocktail | 92 | $23.00 | $2,300 |
| 200ml bottled Mocktail | 13 |  |  |
|  |  |  |  |
|  |  | Sub-Total | $15,093.00 |
|  |  | Service Charge | $1,509.30 |
|  |  | GST | $1,162.16 |
|  |  |  |  |
| Furniture Rental | 1 | $1,500.00 | $1,500.00 |
|  |  |  |  |
|  |  | Sub-Total | $1,500.00 |
|  |  | Service Charge | $150.00 |
|  |  |  |  |
|  |  | Combine Total | $19,414.46 |
|  |  | Rounding | $0.04 |
|  |  | Grand Total | $19,414.50 |